## Slide 1: Agile Approach

## Slide 2: Scrum Agile Team Roles
Product Owner
Works closely with the stakeholders for input
Manages Product Backlog
Scrum Master
Coach
Reports to the Product Owner
Facilitates and leads the Daily Scrum
Developers
Design
Testing
Coding

## Slide 3: Software Development Life Cycle
1. Planning and Analysis
Gather business requirements from the client
Evaluate the feasibility of creating the product
2. Design
Define functions
Define limitations, budget, and time frame
3. Development
Turn software requirements into code
Create database
4. Testing
Software is tested to ensure it meets the requirements
Software is tested to ensure it functions correctly
5. Deployment
Deployed to production and available to end-users
6. Maintenance
Support, bug fixes, and updates

## Slide 4: Waterfall Approach
With the Waterfall Approach, the changes requested would have caused a problem. The Waterfall Approach is linear and does not allow going back and making changes. With the request to change the vacation packages to detox and wellness, we would have needed to stop the project and go back and restart the project from the beginning. This would delay the deployment date past the expected date.

## Slide 5: Waterfall vs Agile Approach
Waterfall
Linear and Sequential
Plan driven
Distinct Goals
Cannot turn back
Agile
Real-time decision making
Small iterations or Springs
Customer provides inputs
Ability to go back to update and make changes

## Slide 6: References
https://www.atlassian.com/agile/scrum/roles
https://www.geeksforgeeks.org/what-is-sdlc-model-and-its-phases/
Charles G. Cobb. The Project Manager’s Guide to Mastering Agile : Principles and Practices for an Adaptive Approach. Wiley, 2015.